## MOM
Meeting Details:
Purpose: | Weekly Meeting for CtrlShift
Facilitator: | Nidhi Gadhari | Date: | 2017-04-11 | Recorder: | Umesh Kumar Toke
Venue: | CT2-5-8870 | Start Time: | 5.00 PM | End Time: | 18:00
Attendees: | Anit M,Amogh D, Ankita B, Vikas B, Umesh T, Vinita P, Jayesh K, KrantiKumar S, ShriKrishn, Neelima
Absentees: | NA
Distribution List: | CtrlShift, Cybage
Agenda of Meeting: | Team Task Status
Points Raised:
Sr. No. | Item | Discussion |  |  | Decisions Taken
1 | Team task status | Team shared their respective status
2 | UX -Custom Reports | Custom Reports |  |  | 1) Annette stated that UX team is working on the custom reports and she had discussion about finanalization of custom reports with the client. 2) They are working on few of the changes that were suggested but they have not finalized yet. Client has informed us to get the requirements and the tool will be finanlised by chethan. 3) Neelima said that Client is thinking about the corelation between metrics he also wants to talk with data scientist expert. Completed VD's and waiting for client review.
3 | UX - Logo | Logo - Blending & Color |  |  | 1) Annette mentioned that the team has no visibility of logo, it will be taken care by the client. 2) Vinay has also mentioned that there are some other internal reports of which team has no visibility thats the reason Vinay said once logo is done he will taking up that. Not clear whether it will further go on. 3) Nidhi suggested to check for the blending on the header of the logo & color before the end date.
3 | UI | Campaign & DMP listing |  |  | 1) Shri is working on campaign module which is on priority 2) Kranti is working DMP listing which is on priority.
3 | QA - Manual Testing | No of bugs and unit testing |  |  | 1)Vinita is doing manual level testing. The no of bugs logged are very high as basic unti testing is not done from their side. 2) Operational release is planned this week but then bugs needs to be fixed by roshan who is not there this week so the client is figuring out how this can be managed, Vinita is continuing with her task. 3) Client suggested Vinita to test as soon as the PR is raised . .
3 | QA - Automation Testing | No of bugs and unit testing |  |  | 1) Client suggested for automation on feature-branch. Amogh stated that changing workflow of github might help to mitigate this problem. Rollbacks are carried out as testing is not done on their end 2) Solution would be to have a release branch 3) Nidhi responded that It is business need that's why they do it in this way. 4) Nidhi suggested to have discussion to which amogh replied the same is planned in future. 5) Nidhi asked about failing test to which amogh replied that it is due to the node not picking up the test case. 6) Amogh will move on to new UX tickets. .
3 | BackEnd | MediaMath & TubeMogul |  |  | 1) Vikas is working on tubemogul 2) Ankita is working with Vikas. She is being assigned with some part of the Vikas's work. 3) Nidhi suggested to have a knowledge sharing session with Meer 4) Umesh is working on sizmek performance report. .
Action items of individual meetings can be listed in the same MOM (in below section) and tracked in subsequent MOMs OR A single template (Action Item Log) can be used for logging and tracking action items from all the meetings
Action Items:
Sr. No | Action Item | Responsible Person | Open since | Expected Completion Date | Revised Completion Date | Actual Completion Date | Status (Open/ In-Progress / Closed/ On-Hold) | Remarks

## Reference (hidden)
Status options: | Open
In-Progress
Closed
On-Hold